SYNTHETIC DEMONSTRATION ONLY

# Corrective Action Plan — Review-ready draft

Not submitted to, approved by, or certified for the United States Government

| Program | Falcon Control Modernization |
| --- | --- |
| Contract | W91XYZ-27-C-0042 |
| Source snapshot | snapshot_mx12_20260727_001 |
| Policy evaluation | dfars-252.225-7052@2026-07-27 |

# Significant supply-chain risk

Covered-country process is restricted

## Evidence-backed cause

Is the material covered?: ndfeb_magnet is covered.
Does the delivery invoke full-chain restrictions?: Delivery is on or after January 1, 2027.
Is a relevant process tied to a covered country?: separation at Baotou Facility 2 — Synthetic (CN); refining at Baotou Facility 2 — Synthetic (CN)
Does an unqualified alternative clear the finding?: An alternative exists but remains unqualified.
Is a government nonavailability determination on record?: Contractor remediation state does not relax the restriction; only a determination under DFARS 225.7018-4 does.

# Immediate containment

Qualify Granite N48SH-equivalent magnet

# Alternative-source qualification

Current finding remains restricted while qualification is in progress.

- ✓ Candidate identified — Supply Chain — 2026-07-08 — complete

- ✓ Commercial data requested — Procurement — 2026-07-22 — complete

- ○ Technical equivalence review — Priya Nair — 2026-08-18 — in progress

- ○ Sample procurement — Procurement — 2026-09-04 — blocked

- ○ Material testing — Materials Lab — 2026-10-12 — not started

- ○ System integration test — Actuator Engineering — 2027-01-15 — not started

- ○ Supplier quality approval — Supplier Quality — 2027-02-12 — not started

- ○ Program approval and production release — Configuration Control Board — 2027-03-31 — not started

# Unknowns and residual risk

Cost, schedule, and lead times are synthetic planning estimates.
Available production capacity remains unverified.
Qualification does not clear the current restricted finding.

# Lineage

Finding finding_magnet_2027_restriction; claims claim_bom_magnet, claim_final_japan, claim_alloying_japan, claim_powder_japan, claim_pressing_japan, claim_magnetization_japan, claim_separation_china, claim_refining_china; evidence ev_bom, ev_pacific_origin, ev_long_river; snapshot snapshot_mx12_20260727_001.